## Overview
SIRA - Deployment Plan
Flutter mobile app + Laravel 11 backend (Nova, Horizon/Redis, Sanctum) ¦ Plan created 13 Jul 2026 ¦ Go-live deadline: Saturday 1 Aug 2026
Environments
Current (source) | https://sira.xpertbot.online - Laravel Forge server; source of user/data migration
QA | https://qa.<your-domain> - AWS EC2 (Nginx, PHP 8.2, MySQL 8, Redis)
Production | https://<your-domain> - AWS EC2 + RDS MySQL + Redis
Mobile | Signed APK distributed via public download link + QR code (S3/CloudFront)
Milestones
Fri 17 Jul 2026 | Infrastructure ready (QA + prod servers, DNS, SSL, backups, monitoring)
Fri 24 Jul 2026 | QA validated - data migrated, UAT signed off
Wed 29 Jul 2026 | Team trained (mobile + web), production deployed & checked
Fri 31 Jul 2026 | Final data migration complete, dry run passed
Sat 01 Aug 2026 | GO LIVE
Fri 07 Aug 2026 | Hypercare ends, decommission plan for old server
Phases
P1 Decisions & Accounts
P2 Infrastructure (AWS)
P3 QA Deploy & Data Migration
P4 APK & Training Prep
P5 Training
P6 Production Go-Live
P7 Post Go-Live
Tasks marked 'Added' are missing points added to the plan (they were not in the original request but are required).

## Schedule
# | Phase | Task | Details | Owner | Start | End | Days | Status | Source
1 | P1 Decisions & Accounts | Define AWS architecture & sizing | Decide region + services: EC2 for QA; EC2 + RDS MySQL 8 + Redis for prod; S3 for uploads & APK hosting. | Ibrahim | Mon 13 Jul | Mon 13 Jul | 1 | Not started | Added
2 | P1 Decisions & Accounts | Secure AWS account | IAM admin user, MFA on root, billing alerts / monthly budget. | Ibrahim | Mon 13 Jul | Mon 13 Jul | 1 | Not started | Added
3 | P1 Decisions & Accounts | Buy domain & plan DNS | Register domain (Route 53 or registrar). Plan subdomains: app/api (prod), qa (QA), www. | Ibrahim | Mon 13 Jul | Tue 14 Jul | 2 | Not started | Requested
4 | P1 Decisions & Accounts | Laravel Nova production license | Nova is licensed per site - confirm the license covers the new production domain before deploying. | Ibrahim | Tue 14 Jul | Tue 14 Jul | 1 | Not started | Added
5 | P1 Decisions & Accounts | Third-party services inventory | Google Maps prod API key (restricted), Firebase prod app (google-services.json), mail provider (SES/SMTP - mail is currently 'log'). Request SES production access early. | Ibrahim | Tue 14 Jul | Tue 14 Jul | 1 | Not started | Added
6 | P2 Infrastructure (AWS) | Provision QA server | EC2: Nginx, PHP 8.2, MySQL 8, Redis, Supervisor for Horizon, cron for the Laravel scheduler. | Ibrahim | Wed 15 Jul | Wed 15 Jul | 1 | Not started | Requested
7 | P2 Infrastructure (AWS) | Provision production server(s) | Same stack sized for production; RDS MySQL recommended; fully separate from QA. | Ibrahim | Wed 15 Jul | Thu 16 Jul | 2 | Not started | Requested
8 | P2 Infrastructure (AWS) | DNS records & SSL certificates | Point QA + prod domains to the servers; HTTPS via Let's Encrypt or ACM; force HTTPS; confirm auto-renewal. | Ibrahim | Thu 16 Jul | Thu 16 Jul | 1 | Not started | Requested
9 | P2 Infrastructure (AWS) | Security hardening | SSH keys only, security groups exposing 80/443 only, firewall, APP_DEBUG=false, Telescope disabled in prod. | Ibrahim | Thu 16 Jul | Thu 16 Jul | 1 | Not started | Added
10 | P2 Infrastructure (AWS) | Automated backups | Nightly DB dumps / RDS snapshots + storage folder to S3, 30-day retention. Test one restore. | Ibrahim | Fri 17 Jul | Fri 17 Jul | 1 | Not started | Added
11 | P2 Infrastructure (AWS) | Monitoring & alerting | Uptime check, CloudWatch alarms (CPU/disk), Laravel error-log alerts, Horizon queue monitoring. | Ibrahim | Fri 17 Jul | Fri 17 Jul | 1 | Not started | Added
12 | P2 Infrastructure (AWS) | Deployment pipeline | Adapt deploy_to_xpertbot.sh for QA & prod: git pull, composer install, migrate, config cache, queue restart. | Ibrahim | Fri 17 Jul | Fri 17 Jul | 1 | Not started | Added
13 | P3 QA Deploy & Data Migration | Deploy backend to QA | QA .env (queue=redis, cache=redis), run migrations, Horizon running, Nova admin reachable over HTTPS. | Ibrahim | Mon 20 Jul | Mon 20 Jul | 1 | Not started | Requested
14 | P3 QA Deploy & Data Migration | Migrate current users & data to QA | Export DB + storage from sira.xpertbot.online, import into QA, verify row counts, logins, roles, client assignments. | Ibrahim | Mon 20 Jul | Tue 21 Jul | 2 | Not started | Requested
15 | P3 QA Deploy & Data Migration | Configure real mail service | Wire SES/SMTP on QA (MAIL_MAILER is currently 'log'); test password reset and notification emails. | Ibrahim | Tue 21 Jul | Tue 21 Jul | 1 | Not started | Added
16 | P3 QA Deploy & Data Migration | QA build of the mobile app | APK pointed at the QA API. Verify login, maps/geolocation, photo upload, FCM push, PDF invoices, Sunmi V3H printing. | Ibrahim | Tue 21 Jul | Wed 22 Jul | 2 | Not started | Requested
17 | P3 QA Deploy & Data Migration | UAT with pilot users | 2-3 real users run full flows on QA: visits, orders, invoices (Standard & Normalisee), return vouchers, printing. | Ibrahim + pilot users | Wed 22 Jul | Fri 24 Jul | 3 | Not started | Added
18 | P3 QA Deploy & Data Migration | Bug fixes & load sanity check | Fix UAT blockers; quick load test on the main API endpoints. | Ibrahim | Thu 23 Jul | Fri 24 Jul | 2 | Not started | Added
19 | P4 APK & Training Prep | Release signing setup | Create the release keystore, configure signingConfig, back the keystore up safely - losing it means no future updates. | Ibrahim | Wed 22 Jul | Wed 22 Jul | 1 | Not started | Added
20 | P4 APK & Training Prep | Public APK download page | Versioned APK on S3/CloudFront (or a web route) + QR code + install guide ('allow unknown sources', Play Protect). | Ibrahim | Thu 23 Jul | Thu 23 Jul | 1 | Not started | Requested
21 | P4 APK & Training Prep | App update strategy | Version-check endpoint in the API + in-app prompt to download the new APK when outdated. | Ibrahim | Fri 24 Jul | Fri 24 Jul | 1 | Not started | Added
22 | P4 APK & Training Prep | Training materials | Mobile user guide, web/Nova admin guide, FAQ and one-page cheat sheets. | Ibrahim | Wed 22 Jul | Fri 24 Jul | 3 | Not started | Added
23 | P4 APK & Training Prep | Trainee accounts on QA | Create accounts & roles for every trainee; seed demo clients and products for exercises. | Ibrahim | Fri 24 Jul | Fri 24 Jul | 1 | Not started | Added
24 | P5 Training | Training - mobile app users | Field agents hands-on on QA: visits, orders, returns, invoice printing. Devices installed from the public link. | Ibrahim + field agents | Mon 27 Jul | Tue 28 Jul | 2 | Not started | Requested
25 | P5 Training | Training - web interface users | Back office & admins: Nova dashboard, client assignment, invoices, return vouchers, reports. | Ibrahim + back office | Tue 28 Jul | Wed 29 Jul | 2 | Not started | Requested
26 | P5 Training | Training feedback & follow-up | Q&A session, collect issues, short re-training where needed. | Ibrahim | Wed 29 Jul | Wed 29 Jul | 1 | Not started | Added
27 | P6 Production Go-Live | Deploy backend to production | Prod .env, Horizon, scheduler cron, Nova; smoke test with a seeded admin account. | Ibrahim | Mon 27 Jul | Tue 28 Jul | 2 | Not started | Requested
28 | P6 Production Go-Live | Go-live checklist & rollback plan | Written checklist (see Checklist sheet) + rollback: keep xpertbot.online warm and re-pointable. | Ibrahim | Wed 29 Jul | Wed 29 Jul | 1 | Not started | Added
29 | P6 Production Go-Live | Final data migration to production | Freeze changes on the old system, fresh export, import to prod, verify. Users keep their passwords. | Ibrahim | Thu 30 Jul | Fri 31 Jul | 2 | Not started | Requested
30 | P6 Production Go-Live | Publish production APK | Final signed build against the prod API, uploaded to the public download link + QR code. | Ibrahim | Thu 30 Jul | Thu 30 Jul | 1 | Not started | Requested
31 | P6 Production Go-Live | Go-live dry run | Full pass on prod: login, visit, order, invoice print, push notification, email. | Ibrahim | Fri 31 Jul | Fri 31 Jul | 1 | Not started | Added
32 | P6 Production Go-Live | GO LIVE | Announce to all users; agents install the prod APK; old system switched to read-only. | Everyone | Sat 01 Aug | Sat 01 Aug | 1 | Not started | Requested
33 | P7 Post Go-Live | Hypercare week | Daily log/Horizon checks, dedicated support channel (WhatsApp), same-day hot-fixes. | Ibrahim | Sat 01 Aug | Fri 07 Aug | 7 | Not started | Added
34 | P7 Post Go-Live | Old server decommission plan | Keep xpertbot.online as fallback for 2 weeks after go-live, then final backup and shutdown. | Ibrahim | Fri 07 Aug | Fri 07 Aug | 1 | Not started | Added

## Gantt
SIRA deployment - 13 Jul to 7 Aug 2026
| JULY 2026 | [18 empty] | AUGUST
| 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
| M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
P1 Decisions & Accounts
1. Define AWS architecture & sizing * | bar: M
2. Secure AWS account * | bar: M
3. Buy domain & plan DNS | bar: M to T
4. Laravel Nova production license * | bar: T
5. Third-party services inventory * | bar: T
P2 Infrastructure (AWS)
6. Provision QA server | bar: W
7. Provision production server(s) | bar: W to T
8. DNS records & SSL certificates | bar: T
9. Security hardening * | bar: T
10. Automated backups * | bar: F
11. Monitoring & alerting * | bar: F
12. Deployment pipeline * | bar: F
P3 QA Deploy & Data Migration
13. Deploy backend to QA | bar: M
14. Migrate current users & data to QA | bar: M to T
15. Configure real mail service * | bar: T
16. QA build of the mobile app | bar: T to W
17. UAT with pilot users * | bar: W to F
18. Bug fixes & load sanity check * | bar: T to F
P4 APK & Training Prep
19. Release signing setup * | bar: W
20. Public APK download page | bar: T
21. App update strategy * | bar: F
22. Training materials * | bar: W to F
23. Trainee accounts on QA * | bar: F
P5 Training
24. Training - mobile app users | bar: M to T
25. Training - web interface users | bar: T to W
26. Training feedback & follow-up * | bar: W
P6 Production Go-Live
27. Deploy backend to production | bar: M to T
28. Go-live checklist & rollback plan * | bar: W
29. Final data migration to production | bar: T to F
30. Publish production APK | bar: T
31. Go-live dry run * | bar: F
32. GO LIVE | bar: S
P7 Post Go-Live
33. Hypercare week * | bar: S to F
34. Old server decommission plan * | bar: F
* = missing point added to the plan ¦ grey columns = weekend ¦ 1 Aug = GO LIVE

## Training Plan
Session | Audience / Topic | Date | Time | Content | Trainer
M1 | Mobile app - Field agents (group A) | Mon 27 Jul | 09:00-12:00 | Hands-on on QA: install from link, login, visits, orders, returns, printing | Ibrahim
M2 | Mobile app - Field agents (group B) | Mon 27 Jul | 14:00-17:00 | Same content as M1 (second group keeps field coverage) | Ibrahim
M3 | Mobile app - practice & Q&A | Tue 28 Jul | 09:00-11:00 | Supervised practice runs, edge cases (offline, GPS off, printer issues) | Ibrahim
W1 | Web interface - back office | Tue 28 Jul | 14:00-17:00 | Nova dashboard, clients & assignment, orders, invoices, return vouchers | Ibrahim
W2 | Web interface - admins (advanced) | Wed 29 Jul | 09:00-12:00 | User & role management, reports, exports, troubleshooting | Ibrahim
F1 | Feedback & wrap-up (all) | Wed 29 Jul | 14:00-15:30 | Q&A, collect issues, confirm go-live readiness with the team | Ibrahim
All sessions run on the QA environment with trainee accounts (task 23). Materials: user guides + cheat sheets (task 22).

## Go-Live Checklist
Done | Check - all must pass before announcing go-live on 1 Aug
NO | DNS resolves and SSL is valid on the production domain (auto-renew confirmed)
NO | APP_ENV=production, APP_DEBUG=false, Telescope disabled
NO | Queues on Redis with Horizon under Supervisor; scheduler cron entry present
NO | Database migrated - row counts match the old system
NO | Spot-check logins: at least one account per role works
NO | Email sending verified (password reset arrives)
NO | Push notification delivered to a real device
NO | Google Maps & geocoding work with the restricted production key
NO | At least one automatic backup has run AND a restore was tested
NO | Monitoring alarms live: uptime, disk, error logs
NO | APK from the public link installs and connects to production
NO | Keystore, .env files and all secrets backed up in a safe place
NO | Rollback plan written; old server (xpertbot.online) untouched and warm
NO | Support channel announced to all users

## Risks
Risk | Level | Mitigation
Single-person dependency (dev + ops + training all on Ibrahim) | High | Timebox tasks, prepare written checklists, delegate training logistics to a manager.
Data migration surprises (schema drift between old prod and current code) | High | The QA migration on 20-21 Jul is a full dry run - fix issues there, not at go-live.
Nova license not valid for the new domain | Medium | Verified on 14 Jul (task 4), weeks before go-live.
APK install blocked on devices (unknown sources / Play Protect) | Medium | Per-device install guide; test on the real device models incl. Sunmi V3H during QA.
SES/mail provider still in sandbox at go-live | Medium | Request production access on 14 Jul - approval can take 24-48h.
Public APK link is open to anyone | Low | App requires login; optionally protect the download page; monitor downloads.
1 August is a Saturday | Low | Cut over Friday 31 Jul evening; go-live announcement Saturday morning with support on duty.
Training no-shows / low adoption | Medium | Two mobile sessions + practice slot; cheat sheets; hypercare support channel.